## Project Plan
PROJECT PLAN
Project Name: |  | Website Redesign Project |  | Project Manager: |  | John Smith
Start Date: |  | 2024-01-01 08:00 |  | End Date: |  | 2024-04-30 07:00
Status: |  | In Progress |  | Overall Progress:
TASK LIST
Task ID | Task Name | Description | Assigned To | Start Date | End Date | Duration | Status | % Complete
T001 | Project Kickoff | Initial project meeting and planning | John Smith | 2024-01-01 08:00 | 2024-01-05 08:00 |  | Completed | 100
T002 | Requirements Gathering | Collect and document all requirements | Sarah Johnson | 2024-01-08 08:00 | 2024-01-19 08:00 |  | Completed | 100
T003 | Design Mockups | Create initial design concepts | Mike Chen | 2024-01-22 08:00 | 2024-02-09 08:00 |  | Completed | 100
T004 | Design Review | Review and approve designs | John Smith | 2024-02-12 08:00 | 2024-02-16 08:00 |  | Completed | 100
T005 | Frontend Development | Develop website frontend | Emily Davis | 2024-02-19 08:00 | 2024-03-22 07:00 |  | In Progress | 65
T006 | Backend Development | Develop backend systems | Robert Lee | 2024-02-19 08:00 | 2024-03-22 07:00 |  | In Progress | 55
T007 | Content Creation | Write and prepare website content | Lisa Brown | 2024-03-01 08:00 | 2024-03-15 07:00 |  | In Progress | 40
T008 | Testing & QA | Comprehensive testing phase | David Wilson | 2024-03-25 07:00 | 2024-04-12 07:00 |  | Not Started | 0
T009 | Deployment | Deploy to production environment | Robert Lee | 2024-04-15 07:00 | 2024-04-22 07:00 |  | Not Started | 0
T010 | Project Closure | Final documentation and handover | John Smith | 2024-04-23 07:00 | 2024-04-30 07:00 |  | Not Started | 0
MILESTONES
Milestone | Target Date |  | Status
Design Approval | 2024-02-16 08:00 |  | 2024-02-16 08:00 |  | Completed
Development Complete | 2024-03-22 07:00 |  |  |  | In Progress
Testing Complete | 2024-04-12 07:00 |  |  |  | Pending
Go Live | 2024-04-30 07:00 |  |  |  | Pending
RESOURCE ALLOCATION
Resource Name |  | Tasks Assigned
John Smith |  | Project Manager |  | 3 |  | 75%
Sarah Johnson |  | Business Analyst |  | 1 |  | 100%
Mike Chen |  | UI/UX Designer |  | 1 |  | 100%
Emily Davis |  | Frontend Developer |  | 1 |  | 100%
Robert Lee |  | Backend Developer |  | 2 |  | 85%
Lisa Brown |  | Content Writer |  | 1 |  | 60%
David Wilson |  | QA Engineer |  | 1 |  | 50%
BUDGET SUMMARY
Category |  | Actual Spent
Design & Development |  | 75000 |  | 48750
Content Creation |  | 15000 |  | 9000
Testing & QA |  | 20000 |  | 0
Project Management |  | 25000 |  | 16250
Miscellaneous |  | 10000 |  | 3500
TOTAL:
Note: This project plan should be updated weekly. All dates and progress percentages should be reviewed and adjusted as needed.