## Project Plan
PROJECT PLAN
Project Name: |  | Website Redesign Project |  |  | Project Manager: |  | Sarah Johnson
Start Date: |  | 2024-01-15 |  |  | End Date: |  | 2024-04-30
Status: |  | In Progress
Task ID | Task Name | Description | Assigned To | Start Date | End Date | Duration | Status | % Complete | Dependencies
T001 | Project Kickoff | Initial project meeting and planning | Sarah Johnson | 2024-01-15 | 2024-01-16 |  | Completed | 100%
T002 | Requirements Gathering | Collect and document all project requirements | Mike Chen | 2024-01-17 | 2024-01-26 |  | Completed | 100% | T001
T003 | Design Mockups | Create wireframes and design mockups | Emily Rodriguez | 2024-01-27 | 2024-02-09 |  | Completed | 100% | T002
T004 | Client Review | Present designs to client for approval | Sarah Johnson | 2024-02-10 | 2024-02-13 |  | Completed | 100% | T003
T005 | Frontend Development | Develop HTML/CSS/JavaScript components | David Kim | 2024-02-14 | 2024-03-15 |  | In Progress | 65% | T004
T006 | Backend Development | Build server-side functionality and APIs | Alex Turner | 2024-02-14 | 2024-03-20 |  | In Progress | 55% | T004
T007 | Content Migration | Migrate existing content to new platform | Jessica Lee | 2024-03-01 | 2024-03-22 |  | In Progress | 40% | T005
T008 | Integration Testing | Test all components and integrations | Mike Chen | 2024-03-21 | 2024-04-05 |  | Not Started | 0% | T005,T006,T007
T009 | UAT & Bug Fixes | User acceptance testing and bug resolution | All Team | 2024-04-06 | 2024-04-20 |  | Not Started | 0% | T008
T010 | Deployment & Launch | Deploy to production and launch website | David Kim | 2024-04-21 | 2024-04-30 |  | Not Started | 0% | T009
PROJECT SUMMARY
Total Tasks: | [5 empty] | Overall Completion:
Completed Tasks: | [5 empty] | Days Elapsed:
In Progress Tasks: | [5 empty] | Days Remaining:
Not Started Tasks:

## Resources
RESOURCE ALLOCATION
Resource Name | Role | Active Tasks | Assigned Tasks
Sarah Johnson | Project Manager | 2 | Project Kickoff, Client Review
Mike Chen | QA Lead | 1 | Requirements Gathering, Integration Testing
Emily Rodriguez | UI/UX Designer | 1 | Design Mockups
David Kim | Frontend Developer | 2 | Frontend Development, Deployment & Launch
Alex Turner | Backend Developer | 1 | Backend Development
Jessica Lee | Content Specialist | 1 | Content Migration

## Milestones
PROJECT MILESTONES
Milestone ID | Milestone Name | Target Date | Status | Description
M1 | Project Approval | 2024-01-16 | Completed | Initial project approval and kickoff
M2 | Design Sign-off | 2024-02-13 | Completed | Client approval of final designs
M3 | Development Phase Complete | 2024-03-20 | In Progress | All development work finished
M4 | Testing Complete | 2024-04-05 | Not Started | All testing phases completed
M5 | Go-Live | 2024-04-30 | Not Started | Website launched to production