## Overview
PROJECT PLAN - OVERVIEW
Project Name: | Digital Transformation Initiative | Start Date: | 2024-01-15
Project Manager: | Sarah Johnson | End Date: | 2024-06-30
Total Budget: |  | Status: | In Progress
PROJECT DASHBOARD
Total Tasks: |  | Overall Progress:
Completed Tasks: |  | Budget Spent:
In Progress: |  | Budget Remaining:
Not Started: |  | Budget Usage:
Team Members: |  | Open Risks:
Total Hours Allocated: |  | High Priority Risks:
Total Hours Used: |  | Milestones Completed:

## Tasks
PROJECT TASKS
Task ID | Task Name | Description | Priority | Assigned To | Start Date | End Date | Duration | Status | % Complete | Dependencies
T001 | Project Initiation | Define project scope and objectives | High | Sarah Johnson | 2024-01-15 | 2024-01-19 |  | Completed | 100%
T002 | Requirements Gathering | Collect stakeholder requirements | High | Michael Chen | 2024-01-22 | 2024-02-02 |  | Completed | 100% | T001
T003 | System Design | Create technical architecture | High | Emily Rodriguez | 2024-02-05 | 2024-02-23 |  | In Progress | 65% | T002
T004 | Database Setup | Configure database infrastructure | Medium | David Park | 2024-02-12 | 2024-02-26 |  | In Progress | 45% | T003
T005 | UI/UX Design | Design user interface mockups | High | Lisa Wong | 2024-02-19 | 2024-03-08 |  | In Progress | 30% | T002
T006 | Frontend Development | Implement user interface | High | James Wilson | 2024-03-11 | 2024-04-12 |  | Not Started | 0% | T005
T007 | Backend Development | Build API and services | High | Michael Chen | 2024-03-04 | 2024-04-19 |  | Not Started | 0% | T004
T008 | Integration Testing | Test system components | Medium | Anna Martinez | 2024-04-22 | 2024-05-10 |  | Not Started | 0% | T006,T007
T009 | User Acceptance Testing | Conduct UAT with stakeholders | High | Sarah Johnson | 2024-05-13 | 2024-05-31 |  | Not Started | 0% | T008
T010 | Documentation | Prepare user and technical docs | Medium | Robert Kim | 2024-05-20 | 2024-06-07 |  | Not Started | 0% | T007
T011 | Training | Train end users on new system | Medium | Lisa Wong | 2024-06-03 | 2024-06-14 |  | Not Started | 0% | T009
T012 | Go-Live | Deploy to production | High | David Park | 2024-06-24 | 2024-06-28 |  | Not Started | 0% | T010,T011

## Resources
RESOURCE ALLOCATION
Team Member | Role | Assigned Tasks | Hours Allocated | Hours Used | Availability %
Sarah Johnson | Project Manager | T001, T009 | 320 | 280
Michael Chen | Senior Developer | T002, T007 | 480 | 420
Emily Rodriguez | Solutions Architect | T003 | 360 | 234
David Park | DevOps Engineer | T004, T012 | 400 | 180
Lisa Wong | UX Designer | T005, T011 | 380 | 114
James Wilson | Frontend Developer | T006 | 420 | 0
Anna Martinez | QA Engineer | T008 | 340 | 0
TOTALS:

## Milestones
PROJECT MILESTONES
Milestone Name | Target Date | Status | Dependencies
Project Kickoff | 2024-01-15 | Complete | T001
Requirements Finalized | 2024-02-02 | Complete | T002
Design Phase Complete | 2024-03-08 | In Progress | T003, T005
Development Phase Complete | 2024-04-19 | Not Started | T006, T007
Testing Complete | 2024-05-31 | Not Started | T008, T009
Documentation Complete | 2024-06-07 | Not Started | T010
Go-Live | 2024-06-28 | Not Started | T012

## Budget
PROJECT BUDGET TRACKING
Category | Allocated | Spent | Remaining | % Used
Personnel Costs | 180000 | 126000
Software Licenses | 45000 | 32000
Hardware & Infrastructure | 65000 | 58000
Training & Development | 25000 | 8000
Consulting Services | 40000 | 28000
Travel & Expenses | 18000 | 9500
Testing & QA | 22000 | 4200
Documentation | 15000 | 3800
Contingency Reserve | 30000 | 0
TOTAL:

## Risks
RISK REGISTER
Risk Description | Probability | Impact | Risk Score | Status | Mitigation Plan
Resource availability issues | Medium | High |  | Open | Maintain backup resource pool and cross-train team members
Scope creep during development | High | High |  | Open | Strict change control process and regular stakeholder reviews
Integration complexity with legacy systems | Medium | Medium |  | Mitigated | Early prototyping and dedicated integration testing phase
Budget overruns | Low | High |  | Open | Weekly budget reviews and contingency reserve allocation
Technology changes during project | Low | Medium |  | Open | Modular architecture design for flexibility
Stakeholder resistance to change | Medium | High |  | Open | Comprehensive change management and training program
Data migration challenges | High | Medium |  | Open | Detailed data mapping and phased migration approach