## Project Plan
PROJECT ROADMAP
Project Name: |  |  | Digital Transformation Initiative
Timeline: |  |  | Q1 2024 - Q4 2024
TASK NAME | OWNER | START DATE | DURATION | STATUS | PROGRESS
Requirements Gathering & Analysis | Sarah Johnson | 2024-01-15 | 3 weeks | Completed
System Architecture Design | Michael Chen | 2024-02-05 | 4 weeks | Completed
Database Schema Development | Emily Rodriguez | 2024-03-01 | 2 weeks | In Progress
Frontend UI/UX Implementation | David Kim | 2024-03-15 | 6 weeks | In Progress
Backend API Development | Jessica Martinez | 2024-03-22 | 5 weeks | In Progress
Integration Testing | Robert Taylor | 2024-04-26 | 3 weeks | Not Started
Security Audit & Compliance | Amanda Wilson | 2024-05-17 | 2 weeks | Not Started
User Acceptance Testing | Christopher Lee | 2024-05-31 | 2 weeks | Not Started
Documentation & Training | Michelle Brown | 2024-06-14 | 3 weeks | Not Started
Production Deployment | James Anderson | 2024-07-05 | 1 week | Not Started
PROJECT SUMMARY
Completed Tasks:
In Progress Tasks:
Not Started Tasks:
✦ Modern Project Planning - Stay Organized, Deliver Excellence ✦