## Project Plan
PROJECT PLAN
Project Name: | Website Redesign Project |  | Start Date: | 2024-01-15 08:00
Project Manager: | John Smith |  | End Date: | 2024-03-31 07:00
# | Task Name | Assigned To | Start Date | End Date | Status
1 | Project Kickoff Meeting | John Smith | 2024-01-15 08:00 | 2024-01-15 08:00 | Completed | 100%
2 | Requirements Gathering | Sarah Johnson | 2024-01-16 08:00 | 2024-01-26 08:00 | Completed | 100%
3 | Design Mockups | Mike Chen | 2024-01-29 08:00 | 2024-02-09 08:00 | In Progress | 75%
4 | Content Creation | Emily Davis | 2024-02-05 08:00 | 2024-02-23 08:00 | In Progress | 50%
5 | Development Phase | Alex Turner | 2024-02-12 08:00 | 2024-03-08 08:00 | Not Started | 0%
6 | Testing & QA | Lisa Wang | 2024-03-11 07:00 | 2024-03-22 07:00 | Not Started | 0%
7 | Client Review | John Smith | 2024-03-25 07:00 | 2024-03-28 07:00 | Not Started | 0%
8 | Launch | Team | 2024-03-31 07:00 | 2024-03-31 07:00 | Not Started | 0%
PROJECT SUMMARY |  |  |  | Total Tasks: | 8
Overall Progress:
Update task status and % complete as the project progresses